## Sheet1
Testing
ID | Group | Text | Implemented In | UI XREF | Testable? | Group 9 | Group 10 | Group 11 | Group 12 | Group 13 | Group 14 | Group 15 | Group 16 | Group 17 | Group 22 | Group 23 | Group 24
R001 | 10 | The page will show the user their username and which game they are in. | requestPlayersUserName(), handleUsernames() | #VALUE! |  | Group 10: TEST Prodecure and Defect Identification is in different spreadsheet; Group 11: The page show the user their username and which game they are in.; Group 12: Not implemented; Testing Group 14: Not Implemented; Testing Group 15: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: Not implemented | cut and paste the screenshot of each page in this part of the spreadsheet, please. use as much space is needed.
R002 | 10 | The page will show the user the other players user name when they have joined. | displayPlayers(), requestAllUsername() | #VALUE! |  | Group 11: The page show the user the other players user name when they have joined.; Testing Group 14: #VALUE!; Testing Group 16: The page is not showing the username of the player who joined, it is just showing Player 1 or player 2; Testing Group 22: Player Id is shown in lobby
R003 | 10 | The page will show the user the two bots in their lobby. | addPlayerToLobby(), toggleEntitySelection() | #VALUE! |  | Group 11: The page show the user the two bots in their lobby.; Testing Group 14: #VALUE!; Testing Group 16: Yes the page shows the 2 bots are in the lobby; Testing Group 22: yes it shows two bots.
R004 | 10 | The page will show 10 lobbies that the user can join which every lobby they want, but can only be in one. | displayLobbies(), refreshLobbies(), joinLobby() | #VALUE! |  | Group 11: The page does notshow 10 lobbies that the user can join which every lobby they want, but can only be in one.; Testing Group 14: #VALUE!; Testing Group 16: Yes the page shows the 10 lobbies that users can join; Testing Group 22: yes it shows the players in lobbies
R005 | 10 | The page will show a go back button for the user to go back to the new account/login page. | handleBackButton() (if implemented) | #VALUE! |  | Group 11: not implemented; Testing Group 14: #VALUE!; Testing Group 16: Yes the page shows the back button but it is not functioning , i.e nothing happens.; Testing Group 22: yes it shows the back button.
R006 | 10 | The page shall gather the information of the user’s username from the page manager in order to show it in the lobby. | requestPlayersUserName(), handleUsernames() |  | not testable | Group 11: not testable; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R007 | 10 | The page shall show all available players in as a list on the Join Game page. | displayPlayers(), selectPlayer() | #VALUE! |  | Group 11: The page does notshow all available players in as a list on the Join Game page.; Group 12: Not implemented; Testing Group 14: Currently Displays no players as it is not implemented; Testing Group 15: Currently Displays no players as it is not implemented; Testing Group 16: Not Implemented; Testing Group 22: not implemented.
R008 | 10 | The page shall show a list of available lobbies that users can join. | displayLobbies(), refreshLobbies() | #VALUE! |  | Group 11: not implemented; Group 12: login page is not working and cannot test; Testing Group 14: Shows the available lobbies; Testing Group 15: Shows the available lobbies; Testing Group 16: Yes the page shows the list of available lobbies; Testing Group 22: login page is not working doesn’t show the lobby
R009 | 10 | The user shall be able to select a lobby to join. | joinLobby() | #VALUE! |  | Group 11: not implemented; Group 12: cannot test, since cannot login; Testing Group 14: #VALUE!; Testing Group 16: Single user is not able to join the lobby, if 2 players/Bot is there then directly enter the game but can't wait in lobby; Testing Group 22: cannot test
R010 | 10 | The page shall show the current status of each lobby (e.g., full, open). | getLobbyStatus(), updateLobbyStatus() | #VALUE! |  | Group 11: not implemented; Group 12: does not show lobby status; Testing Group 14: Does not show lobby Status; Testing Group 15: Shows the available lobbies; Testing Group 16: No the page does not show the current status of the lobby.; Testing Group 22: It doesn't show any status in lobby.
R011 | 10 | The user shall be able to see the number of players currently in each lobby. | displayLobbyPlayerCount() | #VALUE! |  | Group 11: not implemented; Group 12: cannot join, since login page is not working; Testing Group 14: Does not show players in current lobby even if I try to join; Testing Group 15: Does not show players in current lobby even if I try to join; Testing Group 16: Page does not shows the number of players in the lobby; Testing Group 22: It shows the number of player but doesn't allow me to join.
R012 | 10 | The user shall be able to leave a lobby if they wish to join a different one. | leaveLobby(), updateLobbyList() | #VALUE! |  | Group 11: not implemented; Group 12: cannot test, since cannot login; Testing Group 14: Can't leave nor join lobby; Testing Group 15: can join lobby; Testing Group 16: Since there is no any interface for lobby, user cannot leave the lobby; Testing Group 22: Cannot join the lobby
R013 | 10 | The page shall display a "Start Game" button once the user has joined a lobby. | displayStartButton(), startGame() |  | not testable | Group 11: implemented; Group 12: cannot join game, and cannot test; Testing Group 14: Does not show Start Game; Testing Group 15: Does not show Start Game; Testing Group 16: Does not have "Start Game" button; Testing Group 22: no start button.
R014 | 10 | The page shall show an error message if the user tries to join a full lobby. | displayErrorMessage(), checkLobbyAvailability() | #VALUE! |  | Group 11: not implemented; Testing Group 14: Does not show error as unable to join lobby; Testing Group 15: unable to test; Testing Group 16: No any error message; Testing Group 22: no error message after I press any key.
R015 | 10 | The user shall be able to view the usernames of all players in the lobby. | displayPlayersInLobby() | #VALUE! |  | Group 11: not implemented; Testing Group 14: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: not implemented.
R016 | 10 | The user shall be able to send a message to other players in the lobby. | sendMessage(), receiveMessages() |  |  | Group 11: not implemented; Testing Group 14: Not Implemented; Testing Group 15: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: not implemented.
R017 | 10 | The page shall refresh automatically to update the list of players and lobbies every few seconds. | refreshPage() | #VALUE! |  | Group 11: non testable; Testing Group 14: When clicking button nothing happens and nothing is sent in the console; Testing Group 15: When clicking button nothing happens and nothing is sent in the console; Testing Group 16: Color of the button changes but button has no function; Testing Group 22: color the changes button no function after T press of key.
R018 | 10 | The user shall be able to select a bot to add to their game, if available. | addBot(), toggleEntitySelection() | #VALUE! |  | Group 11: non testable; Testing Group 14: Able to add bots by clicking them; Testing Group 15: Able to add bots by clicking them; Testing Group 16: User can add the Bot I/BotII; Testing Group 22: user add bot botii BotII after T press can key.
R019 | 10 | The page shall allow the user to toggle between viewing available lobbies and their current lobby. | toggleLobbyView() | #VALUE! |  | Group 11: not implemented; Testing Group 14: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: not implemented.
R020 | 10 | The page shall display a "waiting for players" message if the user is in a lobby but the game hasn’t started yet. | displayWaitingMessage() | #VALUE! |  | Group 11: not implemented; Testing Group 14: Not Implemented; Testing Group 16: No any waiting message was displayed; Testing Group 22: No waiting message in displayed in lobby.
R021 | 10 | The user shall be able to see which lobby they are currently in. | displayCurrentLobby() | #VALUE! |  | Group 11: not implemented; Testing Group 14: Not Implemented; Testing Group 16: Since there is no any interface for lobby, user cannot see which lobby they are in; Testing Group 22: Not Implemented.
R022 | 10 | The user shall be able to leave the current game and return to the lobby selection page. | leaveGame(), returnToLobbySelection() | #VALUE! | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: User are able to leave the game but it goes to create account/login page; Testing Group 22: Not Implemented.
R023 | 10 | The page shall indicate when the game has started. | startGameIndicator() | #VALUE! | not testable | Group 10: not implemented; Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: Can not test since Login page is not working.
R024 | 10 | The page shall provide a visual indicator of the user’s current progress in the lobby (e.g., loading bar). | displayProgress() | #VALUE! | not testable | Group 10: not implemented; Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: Since there is no any interface for lobby, user cannot see any progress; Testing Group 22: Not Implemented.
R025 | 10 | The page shall display the users in the particular game session they have choosen to be in. | displayUsers() | #VALUE! | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: Can not test since Login page is not working.
R026 | 10 | The page shall register when a button is being pressed and send the message in order to accept the receving message. | msg() | #VALUE! | not testable | Group 10: removed msg() and used socket.send() instead; Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R027 | 10 | The page shall show the user when players have been selected and enables the Join Game button when both players have been selected. | updateSelectionDisplay() | #VALUE! |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: Page is not showing any users; Testing Group 22: not testable; Testing Group 23: not testable
R028 | 10 | The page shall allow the user to choose to wait for other players by selecting the wait button. | waitLobby() | #VALUE! |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 16: Not Implemented; Testing Group 22: not testable; Testing Group 23: not testable
R029 | 17 | BotI class shall encapsulate all methods needed for Bot I's implementation. | BotI |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R030 | 17 | Methods in the BotI class shall rely upon "Position" and "Move" objects (which are implemented by other groups). | BotI |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R031 | 17 | Bot I shall communicate to the game by having gameManager call onUserMove() and returning to it a Move object. | onUserMove() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R032 | 17 | GameManager shall notify Bot I that it's the bot's turn by calling onUserMove, where the current 8x8 board is passed as an argument. | onUserMove() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R033 | 17 | It shall become Bot I's turn as soon as the user has made a move. | onUserMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R034 | 17 | Upon notification from GameManager that it's the bot's turn, Bot I shall respond in full in no more than 5 seconds. | BotI |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: Bot is not responding; Testing Group 22: not testable; Testing Group 23: not testable
R035 | 17 | The bot shall generate a complete list of available (legal) standard moves before determining which move to make. | getAvailableMoves(), getAvailableStandardMoves() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: Bot is not showing any legal moves; Testing Group 22: not testable; Testing Group 23: not testable
R036 | 17 | The bot shall generate a complete list of available (legal) capture moves before determining which move to make. | getAvailableMoves(), getAvailableCaptureMoves() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: Bot is not showing any legal moves; Testing Group 22: not testable; Testing Group 23: not testable
R037 | 17 | Lists of available (legal) moves (standard & capture moves) will be stored in two ArrayLists. | getAvailableMoves() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R038 | 17 | The bot shall only consider legal moves. | validateStandardMove(), validateCaptureMove |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R039 | 17 | When determining possible/legal moves, the program shall always ensure that the potential move falls within bounds of the board (8x8). | withinBounds() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R040 | 17 | Capture moves shall only consist of a single jump (not multiple jumps/hops as in traditional checkers). | getAvailableCaptureMoves() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: Not Implemented; Testing Group 22: not testable; Testing Group 23: not testable
R041 | 17 | The game is done when there are no legal moves available. | onUserMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable since every piece has been moving illegally; Testing Group 22: not testable; Testing Group 23: not testable
R042 | 17 | If Bot I has capture move(s) available, these shall hold first priority when choosing a move to make. | generateMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: Not testable; Testing Group 22: not testable; Testing Group 23: not testable
R043 | 17 | If Bot I has multiple capture moves available to make, one shall be chosen at random. | generateMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not testable since every piece has been moving illegally; Testing Group 22: not testable; Testing Group 23: not testable
R044 | 17 | If Bot I has standard move(s) available and no capture move(s), these shall hold second priority when choosing a move to make. | generateMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not implemented; Testing Group 22: not testable; Testing Group 23: not testable
R045 | 17 | If Bot I has multiple stadard moves available to make, one shall be chosen at random. | generateMove() |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Not Testable Since it has not been implemented; Testing Group 16: not implemented; Testing Group 22: not testable; Testing Group 23: not testable
R046 | 17 | If Bot I has no available moves to make, generateMove() shall return null. | generateMove() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R047 | 17 | When evaluating the board (char [][]), Bot I shall consider 'o' as Bot I's standard pieces, 'O' as Bot I's king pieces, 'x' as the user's standard pieces, and 'X' as the user's king pieces. | BotI |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R048 | 14 | The results of every game played will be stored into a database into rows and columns, and shall be used for building the contents of the leaderboard. | DB.java |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the Database.db file 4) Observe either the user or match database is split into rows and columns | Group 11: Can not test since Login page is not working; Testing Group 14: #VALUE!; Testing Group 22: not testable
R049 | 14 | The Database shall utilize the SQLite database management system for local data storage. | DB.java |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R050 | 14 | The database shall record when the game starts or ends |  |  | Not Implemented as deemed not nescessary | Group 11: Can not test since Login page is not working; Testing Group 14: Not Implemented; Testing Group 22: not testable
R051 | 14 | The Leaderboard shall be based on rating system/ELO |  |  | Duplicate | Group 11: Can not test since Login page is not working; Testing Group 14: Duplicate; Testing Group 22: not testable
R052 | 14 | The databse shall be able to Save and Load Games that may have lost connection | setBoardstate() , getBoardstate() |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the Database.db file 4) Click on the Match History Database 5) Check to see if the BoardState is saved in the 4th column | Group 11: Can not test since Login page is not working; Testing Group 14: #VALUE!; Testing Group 22: not testable
R053 | 14 | Store and get the Current Position | setBoardstate() , getBoardstate() |  | Duplicate | Group 11: Can not test since Login page is not working; Testing Group 14: duplicate; Testing Group 22: not testable; Testing Group 23: duplicate
R054 | 14 | store username, password, and email | getUsername() , getPassword() , getEmail() |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the Database.db file 4) Click on the User Database 5) Check to see if the Username (2nd column), Email (3rd), and Password (4th) are in the correct spots | Group 11: Can not test since Login page is not working; Testing Group 14: #VALUE!; Testing Group 22: not testable
R055 | 14 | allow user to set username, password and email | setUsername() , setPassword() , setEmail() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R056 | 14 | The Database shall track the number of wins and losses per player based on game outcomes. | DB.java |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the Database.db file 4) Click on the User Database 5) Check to see if the Wins (5th column) and the Losses (6th) are being stored | Group 11: Can not test since Login page is not working; Testing Group 14: #VALUE!; Testing Group 22: not testable
R057 | 14 | The Database shall calculate a player's ELO score using win/loss data based on game outcomes | calculateElo() |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the PlayerInfo.java file 4) Scroll down until calculateElo() function is found | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: not testable
R058 | 14 | The Database shall allow setting and retrieving the game's board state | setBoardstate() , getBoardstate() |  | Duplicate | Group 11: Can not test since Login page is not working; Testing Group 14: duplicate; Testing Group 22: not testable; Testing Group 23: duplicate
R059 | 14 | The Database shall give the Provide User Id | getPlayerIdByUsername() |  | 1) download SQLite Viewer Extension in VSCode 2) go to .\checkers\src\main\java\uta\cse3310\DB\ 3) Click on the DB.java file 4) Scroll down until getPlayerIdByUsername() function is found | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: not testable
R060 | 14 | The Database shall give the Time elapsed |  |  | Not Implemented as deemed not nescessary | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: not testable
R061 | 14 | The Database shall give the current leaderboard positions |  |  | Will be done by Leaderboard Team | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: not testable
R062 | 14 | The database shall Not have any duplicate emails or usernames (not testable) | DB.java |  | Not Testable as it is done automatically before adding to DB | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 22: not testable; Testing Group 23: not testable
R063 | 11 | The Game should have 8 x 8 array checkers board. | createBoard() |  | not testable | Group 9: PASS, TC063; Testing Group 14: not testable; Testing Group 22: Not testable, Login page error.; Testing Group 23: not testable
R064 | 11 | The board should display 24 checkers (12 red and 12 black) at the start of the game. | createBoard() |  |  | Group 9: PASS, TC064; Group 11: Displays the board; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: Not testable, Login page error.
R065 | 11 | Pieces should be clearly distinguishable by color for two players. | .red .blue |  |  | Group 9: PASS, TC065; Group 11: display 24 checkers (12 red and 12 black) at the start of the game.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: Not testable, Login page error.
R066 | 11 | The board should support different themes that players can choose from. | toggleTheme |  |  | Group 9: PASS, TC066; Group 11: clearly distinguishable by color for two players.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: Not testable, Login page error.
R067 | 11 | When a piece reaches the last row, it should become a King and be visually distinct. | executeValidMove(), .king |  |  | Group 9: PASS, TC067; Group 11: not implemented; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R068 | 11 | Players should be able to move pieces by dragging and dropping. | createPiece() |  |  | Group 9: FAIL, TC068; Group 11: it become a King and bis visually distinct.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: not working; Testing Group 22: Not testable, Login page error.
R069 | 11 | The game should validate whether a move is legal, and prevent invalid moves. | socket.send() |  |  | Group 9: PASS, TC069; Group 11: validate whether a move is legal, and prevent invalid moves.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R070 | 11 | The game should highlight valid moves when a piece is selected. |  |  |  | Group 9: PASS, TC070; Group 11: Higlihts the selected piece; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: Not testable, Login page error.
R071 | 11 | When it is not the player’s turn, their own pieces should be faded or unclickable, while the opponent's pieces are highlighted, and vice versa. |  |  |  | Group 9: FAIL, TC071; Group 11: not implemented; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R072 | 11 | The game should track and display the number of pieces captured. |  |  |  | Group 9: FAIL, TC072; Group 11: not implemented; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R073 | 11 | The game should indicate whose turn it is at all times. | displayPlayerTurn() |  |  | Group 9: PASS, TC073; Group 11: not implemented; Testing Group 14: Can not test since Login page is not working; Testing Group 15: not implemented; Testing Group 22: Not testable, Login page error.
R074 | 11 | The game should provide clear win/loss/draw notifications at the end of a match. | displayEndState(endOfGameState), alert() |  |  | Group 9: FAIL, TC074; Group 11: Provides a win and loss sittuation; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R075 | 11 | A move history should be maintained, allowing players to view previous game states. |  |  |  | Group 9: FAIL, TC075; Group 11: history is be maintained, allowing players to view previous game states.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R076 | 11 | The board should display a timer to track the duration of the game. | drawTimer() |  |  | Group 9: FAIL, TC076; Group 11: Displays the time; Testing Group 14: Can not test since Login page is not working; Testing Group 15: not implemented; Testing Group 22: Not testable, Login page error.
R077 | 11 | Players should have the option to restart the game after it ends. | location.reload() |  |  | Group 9: FAIL, TC077; Group 11: There is a option to resign and start over; Testing Group 14: Can not test since Login page is not working; Testing Group 15: not implemented; Testing Group 22: Not testable, Login page error.
R078 | 11 | The game should support username input and display for both players. | getPlayerdata() |  |  | Group 9: FAIL, TC078; Group 11: It displays the usrs as player 1 and 2; Testing Group 14: Can not test since Login page is not working; Testing Group 15: display implemented; Testing Group 22: Not testable, Login page error.
R079 | 11 | A sound effect should play when a piece is moved. | soundManager.playsound() |  |  | Group 9: PASS, TC079; Group 11: Sound is there; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R080 | 11 | A distinct sound effect should play when a piece is kinged. | soundManager.playsound() |  |  | Group 9: PASS, TC080; Group 11: A distinct sound effect should play when a piece is kinged.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R081 | 11 | A different sound effect should play when a piece is captured. | soundManager.playsound() |  |  | Group 9: PASS, TC081; Group 11: A different sound effect should play when a piece is captured.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves do not register; Testing Group 22: Not testable, Login page error.
R082 | 11 | Players should be able to toggle sound effects on or off. | soundToggle() |  |  | Group 9: PASS, TC082; Group 11: Players should be able to toggle sound effects on or off.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: implemented; Testing Group 22: Not testable, Login page error.
R083 | 11 | Diagonally placement for the checkers. | createBoard() |  |  | Group 9: PASS, TC083; Group 11: Diagonally placement for the checkers.; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R084 | 11 | A sound effect should play at the beginning of a game | soundManager.init() |  |  | Group 9: FAIL, TC084; Group 11: A sound effect should play at the beginning of a game; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R085 | 11 | A sound effect should play when a game is won | soundsManager.playSound() |  |  | Group 9: FAIL, TC085; Group 11: A sound effect should play when a game is won; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R086 | 11 | A sound effect should play when a game is lost | soundsManager.playSound() |  |  | Group 9: FAIL, TC086; Group 11: A sound effect should play when a game is lost; Testing Group 14: Can not test since Login page is not working; Testing Group 15: implemented; Testing Group 22: Not testable, Login page error.
R087 | 11 | A sound effect should play when a game is drawn | soundsManager.playSound() |  |  | Group 9: FAIL, TC087; Group 11: A sound effect should play when a game is drawn; Testing Group 14: Can not test since Login page is not working; Testing Group 15: implemented; Testing Group 22: Not testable, Login page error.
R088 | 11 | A sound effect should play when a player recieves a draw proposal | soundsManager.playSound() |  |  | Group 9: FAIL, TC088; Group 11: A sound effect should play when a player recieves a draw proposal; Testing Group 14: Can not test since Login page is not working; Testing Group 15: not implemented; Testing Group 22: Not testable, Login page error.
R089 | 11 | Players should be able to adjust the volume of sound effects. | soundsManager.playSound() |  |  | Group 9: FAIL, TC089; Group 11: not implemented; Testing Group 14: Can not test since Login page is not working; Testing Group 15: no slider bar but system sound adjustment can be considered I guess; Testing Group 22: Not testable, Login page error.
R090 | 11 | The move history of the active game in play should in store in a linked list on the html alongside the turn order. On the main page there should be two buttons, one to go move backwards in the game history and another to go a move forward in the game history. |  |  |  | Group 9: FAIL, TC090; Group 11: not testable; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R091 | 11 | The move history of the game in play should be displayed in checkers notation |  |  |  | Group 9: PASS, TC091; Group 11: The move history of the game in play should be displayed in checkers notation; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable, Login page error.
R092 | 11 | A move that is made by the player (Whether it would be dragged or clicked), will be sent to the page manager system for checking if the valid move is legal or not. | cell.addEventListener() |  | not testable | Group 11: A move that is made by the player will be sent to the page manager system for checking if the valid move is legal or not.; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R093 | 11 | The usernames for each player (or bot) shall be recieved by the pagemanager | getPlayerdata() |  | not testable | Group 11: not testable; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R094 | 11 | If a bot is in game, a unique tag shall be displayed for them, replacing where the ranking would normally be displayed. | getPlayerdata() |  |  | Group 11: not testable
R095 | 11 | For the themes, a hashmap shall be used for storage of themes |  |  | not testable | Group 11: not testable; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: testable testable
R096 | 11 | The ranking of each player shall be displayed by their username, this data will be recived from the page manager system | getPlayerdata() |  |  | Group 9: FAIL, TC096; Group 11: Can not test since Login page is not working; Group 12: Login page is not opening; Testing Group 14: Can not test since Login page is not working; Testing Group 22: no.
R097 | 11 | Once a move has been verified that it is legal or not via data from the page manager. The gameboard will update with the new positions, if the move was illegal the, the attempted to be moved piece will return to its previous position | executeValidMove() |  |  | Group 9: PASS, TC097; Group 11: not testable; Testing Group 14: Can not test since Login page is not working; Testing Group 22: , Login page error.
R098 | 11 | There shall be a resignation button for when a player wishes to resign | resignbtn |  |  | Group 9: PASS, TC098; Group 11: resignation button for when a player wishes to resign; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: , Login page error.
R099 | 11 | Clicking the resignation button will require a second conformation click. | resignbtn |  |  | Group 9: PASS, TC099; Group 11: Clicking the resignation button will require a second conformation click.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: , Login page error.
R100 | 11 | When a piece moves multiple times in a single turn, there shall be a small visual update delay between each move the moving piece captures during that turn. |  |  |  | Group 9: FAIL, TC100; Group 11: When a piece moves multiple times in a single turn, there shall be a small visual update delay between each move the moving piece captures during that turn.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: cannot be tested as moves not registered; Testing Group 22: , Login fage error.
R101 | 11 | Both proposing and accepting a draw will require a second conformation click when clicked. | drawBtn |  |  | Group 9: PASS, TC101; Group 11: Both proposing and accepting a draw will require a second conformation click when clicked.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: , Login page error.
R102 | 11 | When a player clicks the draw button, on or off their turn, the opposing player will be notified that they are being proposed a draw. | drawBtn |  |  | Group 9: FAIL, TC102; Group 11: When a player clicks the draw button, on or off their turn, the opposing player will be notified that they are being proposed a draw.; Testing Group 14: Can not test since Login page is not working; Testing Group 22: , Login fage error.
R103 | 11 | There shall be a draw button for when a player wishes to propose a draw | drawBtn |  |  | Group 9: PASS, TC103; Group 11: There is a draw button for when a player wishes to propose a draw; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: , Login page error.
R104 | 11 | The game should automatically restart when a player resigns. | resignbtn |  |  | Group 9: FAIL, TC104; Group 11: The game automatically restart when a player resigns.; Testing Group 14: Can not test since Login page is not working; Testing Group 22: , Login fage error.
R105 | 11 | The game should automatically restart when a player ACCEPTS a proposed draw. | drawBtn |  |  | Group 9: FAIL, TC105; Group 11: The game automatically restart when a player ACCEPTS a proposed draw.; Testing Group 14: Can not test since Login page is not working; Testing Group 22: , Login fage error.
R106 | 11 | When a draw is proposed there will be a 10 second timer for the draw to be either confirmed or declined. | drawBtn |  |  | Group 9: PASS, TC106; Group 11: When a draw is proposed there is a 10 second timer for the draw to be either confirmed or declined.; Testing Group 14: Can not test since Login page is not working; Testing Group 15: #VALUE!; Testing Group 22: , Login page error.
R107 | 11 | The recently moved piece should be highlighted briefly. | drawBtn |  |  | Group 9: FAIL, TC107; Group 11: The recently moved piece is highlighted briefly.; Testing Group 14: Can not test since Login page is not working; Testing Group 22: , Login fage error.
R108 | 24 | Pieces shall not overlap each other. | GamePlay() |  | GP-003 | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: invalid move; Testing Group 22: invalid move after W press move key.; Testing Group 24: #VALUE!
R109 | 24 | Regular pieces shall become king pieces once they reach the opponents edge. | promotePiece() |  | DUPLICATE/ REDUNDANTELY CODED | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: Move a regular piece to the opponent’s last row; Testing Group 22: move regular to opponent last row after W press a key.
R110 | 24 | Normal Pieces shall only move towards the opponent. | GamePlay() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: Move a red regular piece backward; Testing Group 22: move red piece backward after W press a key.
R111 | 24 | King Pieces shall be able to move and capture both forward and backward. | GamePlay() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: Move a king piece backward; Testing Group 22: move king backward backward after W press a key.
R112 | 24 | Pieces shall only be on "dark" squares and within the bounds of the board. | isInBounds() |  | GP-002 | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: Move to a light square; Testing Group 22: move a square square after W press to key.
R113 | 24 | Pieces shall not jump over or capture pieces of the same team. | isSameTeam() |  | GP-003 | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: not testable; Testing Group 22: not testable after W press testable key.; Testing Group 24: #VALUE!
R114 | 24 | The function shall send the updated table state to Game Termination if the move is valid. | notifyTermination() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.
R115 | 24 | The function shall return a boolean back to Game Manager. | isValidMove() |  | GP-001 | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.; Testing Group 24: #VALUE!
R116 | 24 | The function shall receive current board state and the move being made from Game Manager. | GamePlay() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: show current board; Testing Group 22: show board board after W press current key.
R117 | 24 | A piece shall only capture an opponent's piece if it makes a diagonal move over the opponent’s piece to a free empty space. | isJump() |  | GP-004 | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 16: show current board; Testing Group 22: show board board after W press current key.; Testing Group 24: #VALUE!
R118 | 24 | The current board state's data structure the class will be receiving is a 2D integer array from Game Manager. | GamePlay() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: show current board; Testing Group 22: Not testable.
R119 | 24 | The class will receive the proposed move with an array of integers to hold the coordinates of the piece and where it will end up. | GamePlay() |  | not testable | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: show current board; Testing Group 22: Not testable.
R120 | 24 | The class will include a function that receives a proposed move and return back if the move is diagonal from it's current position called isDiagonal() | isDiagonal() |  | GP-001 | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.; Testing Group 24: #VALUE!
R121 | 24 | The pieces shall only move diagonally. | isDiagonal() |  | GP-001 | Group 11: Can not test since Login page is not working; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.; Testing Group 24: #VALUE!
R122 | 24 | The isDiagonal() function will verify whether a move is diagonal by comparing the coordinates of the "from" and "to" positions. It calculates the difference between their x and y values and checks that both differences are exactly ±1, indicating a valid diagonal step. | isDiagonal() |  | GP-001 | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.; Testing Group 24: #VALUE!
R123 | 24 | The isInBounds() function will check if the destination coordinates of a move are within the 8×8 board limits. It returns true if both x and y of the "to" position are between 0 and 7, inclusive. | isInBounds() |  | GP-002 | Group 11: Can not test since Login page is not working; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: Can not test since Login page is not working.
R124 | 9 | All input fields should be filled out by the user and the system should not allow submission with empty values. | class: inputValidator¦ functions: validateUsername(), validatePassword(), validateEmail() |  |  | Group 9: PASS, TC124; Group 11: Pass; Testing Group 14: Can not test since Login page is not working; Testing Group 16: #VALUE!; Testing Group 22: VALUE! after W press LUE key.
R125 | 9 | The error messages should be displayed for invalid inputs. | class: inputValidator ¦ function: displayError() | REDUNDANT |  | Group 11: Duplicate; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.
R126 | 9 | Username should be at least 4 characters long and at most 20 characters. | class: inputValidator ¦ function: validateUsername() |  |  | Group 9: PASS, TC126; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.; Testing Group 23: #VALUE!
R127 | 9 | Username should only contain letters, numbers, and underscores. | class: inputValidator ¦ function: validateUsername() |  |  | Group 9: PASS, TC127; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.; Testing Group 23: #VALUE!
R128 | 9 | Username should not contain spaces and special characters (except _) | class: inputValidator¦ function: validateUsername() | REDUNDANT |  | Group 11: Duplicate; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.
R129 | 9 | The password should be at least 8 characters long. | class:inputValidator ¦ function: validatePassword() |  |  | Group 9: PASS, TC129; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.
R130 | 9 | The password should contain at least one uppercase letter, one lowercase letter, one number, and one special character. | class: inputValidator ¦ function: validatePassword() |  |  | Group 9: PASS, TC130; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.; Testing Group 23: #VALUE!
R131 | 9 | Email should be a valid email format. | class: inputValidator ¦ function: validateEmail() |  |  | Group 9: PASS, TC131; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.; Testing Group 23: #VALUE!
R132 | 9 | Duplicate usernames should not be allowed. | socket.onMessage() |  |  | Group 9: PASS, TC132; Group 11: Cannot test login page error; Testing Group 16: #VALUE!; Testing Group 22: Shows whats error in red letter, if you type wrong format.
R133 | 9 | The system shall contain a text field for an existing user to input their existing username. | class: form ¦ input type: text |  |  | Group 9: PASS, TC133; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R134 | 9 | The system shall contain a text field for an existing user to input their existing password. | class: form ¦ input type: text |  |  | Group 9: PASS, TC134; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R135 | 9 | The system shall include a "Login" button which submits the data the user has entered into the text fields (Req. 133-134) | class: form ¦ button |  |  | Group 9: PASS, TC135; Group 11: Cannot test login page error; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R136 | 9 | The system shall contain a text field for new users to enter a unique username. | class: form ¦ input type: text |  |  | Group 9: PASS, TC136; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R137 | 9 | The system shall contain an encrypted text field for new users to enter a valid e-mail address to register their new account. | class: form ¦ input type: email |  |  | Group 9: PASS, TC137; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R138 | 9 | The system shall contain a text field for new users to enter a password that is connected to their username. | class: form ¦ input type: text |  |  | Group 9: PASS, TC138; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R139 | 9 | The system shall contain an encrypted text field for new users to confirm their new password. | class: form ¦ input type: text |  |  | Group 9: PASS, TC139; Group 11: #VALUE!; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R140 | 9 | The system shall include a "Create Account" button which submits the data the user has entered into the text fields [Req. 136-139]. | class: form ¦ button |  |  | Group 9: PASS, TC140; Group 11: Cannot test login page error; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R141 | 9 | The system shall throw an exception to the user in red text, if the username has incompatible ASCII characters. | redundant requirement (similar to [Req. 21] )is deprecated | REDUNDANT to [R127] |  | Group 11: Duplicate; Testing Group 22: Passed the test.
R142 | 9 | The system shall throw an exception to the user in red text, when the username does not exist in the Database | function: validateLogin() {inputValidator.displayErrorMsg(), JSON.Stringify} |  |  | Group 9: PASS, TC142; Group 11: Pass; Testing Group 14: Can not test since Login page is not working; Testing Group 16: #VALUE!; Testing Group 22: Not testable
R143 | 9 | The system shall throw an exception to the user in red text, when the password does not match with the password in the username object. | function: validateLogin() {inputValidator.displayErrorMsg()} |  |  | Group 9: PASS, TC143; Group 11: Pass; Testing Group 14: Can not test since Login page is not working; Testing Group 16: #VALUE!; Testing Group 22: Not testable
R144 | 9 | The system shall throw an exception to the user in red text, when invalid characters are used in the Username sign up text box. [Req. 127] | function:validateSignup() {inputValidator.validateUsername() ¦ inputValidator.displayError()} |  |  | Group 9: PASS, TC144; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R145 | 9 | The system shall throw an exception to the user in red text, when an invalid email is submitted in the email text box. [Req. 131] | function:validateSignup() {inputValidator.validateEmail() ¦ inputValidator.displayError()} |  |  | Group 9: PASS, TC145; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R146 | 9 | The system shall throw an exception to the user in red text, when an invalid character is saved in the Password text box. | needs to be deprecated as there is no specific requirement for Password characters | NOT IMPLEMENTED IN CODE |  | Group 11: Not Implemented; Testing Group 22: Passed the test.
R147 | 9 | The system shall throw an exception to the user in red text, when the password string does not match the confirmed password string. | function:validateSignup() {inputValidator.displayError()} |  |  | Group 9: PASS, TC147; Group 11: Pass; Testing Group 16: #VALUE!; Testing Group 22: Passed the test.
R148 | 22 | The Bot II shall follow all official rules of English draughts, including movement, capturing, promotion, and forced jumps. | BotII.java (onUserMove, getLegalMoves, findCaptureOpportunity) |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not testable
R149 | 22 | The Bot II shall be capable of playing against Bot I without any human intervention. | BotII.java (onUserMove) |  |  | Group 11: Can not test since Login page is not working; Testing Group 14: Can not test since Login page is not working; Testing Group 22: Not Testable.
R150 | 22 | The Bot II shall receive the current game state, including legal moves and board position, from the Game Manager through methods. | BotII.java (onUserMove - receives char[][] board) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R151 | 22 | The Bot II shall use a distinct playing strategy from Bot I, maybe defensive, offensive depending on what style Bot I use. | BotII.java (evaluateBoard, isForwardMove, findSafeMove) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R152 | 22 | The Bot II shall communicate only through Java method calls with the Game Manager. | BotII.java (onUserMove only) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R153 | 22 | The Bot II shall be triggered only by method calls from the Game Manager to perform a move when it is Bot II turn. | BotII.java (onUserMove) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R154 | 22 | The Bot II shall return its move decision to the Game Manager after receiving the game state. | BotII.java (onUserMove) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R155 | 22 | The Bot II shall return a valid Move object in the exact format expected by the Game Manager’s interface. | BotII.java (new Move(...)) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R156 | 22 | The Bot II shall evaluate the board based on number of pieces, kings, and control of center | BotII.java (evaluateBoard, countPieces, board scanning logic) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R157 | 22 | The Bot II shall prioritize offensive strategies such as capturing when evaluation score is high | BotII.java (prioritizeOffense, findCaptureOpportunity) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R158 | 22 | The Bot II shall prioritize defensive strategies such as blocking and safe moves when under threat | BotII.java (prioritizeDefense, findSafeMove, isForwardMove) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R159 | 22 | The Bot II shall be able to determine legal moves | BotII.java (getLegalMoves, makeValidMove, isWithinBoard) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R160 | 16 | Must receive moves from page maneger or gameplay | Gamefile/manager.GameManager / receiveMove() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R161 | 16 | Must vailidate each move played | Gamefile/rules.Gameplay / validateMove() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R162 | 16 | Must update current state of the game | Gamefile/manager.GameManager / updateGameState() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R163 | 16 | Manege multiple activies at once | Gamefile/manager.GameManager / manageSessions() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R164 | 16 | Must store the sate of the game | Gamefile/storage.GameStateStore / saveState() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R165 | 16 | Must Comparair each move with the rules of the game with Game play | Gamefile/rules.Gameplay / compareWithRules() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: te gamefile/rules gameplay .
R166 | 16 | Must reject invalid moves | Gamefile/manager.GameManager / handleInvalidMove() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: te gamefile/manager game manager .
R167 | 16 | Log all moves made durning the with game play | Gamefile/logging.GameLogger / logMove() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: te gamefile/logging game logger.
R168 | 16 | Diplay log of the moves made in the game | Gamefile/ui.MoveLogUI / displayLogs() |  |  | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 16: not testable; Testing Group 22: , Login noge error.
R169 | 16 | Communicate with Page maneger, Bot 1 and bot 1, Pair up and Game play | Gamefile/pairup.PairUp / sendToModule(String target) |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: te gamefile/pairup pair up .
R170 | 16 | Send moves to Bot1 and Bot 2 | Gamefile/bot.BotOne / sendMoveToBot(int botId) |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: te gamefile/bot bot one .
R171 | 16 | Page Manager should support retry logic for failed communications | Gamefile/page.PageManager / retryCommunication() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R172 | 16 | Must communicate with the Pair Up module to assign users to games | Gamefile/pairup.PairUp / assignPlayers() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R173 | 16 | Must route requests and responses to/from the Game Play module | Gamefile/play.GamePlay / routeToGamePlay() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R174 | 16 | Must communicate with Bot 1 for automated player moves when required | Gamefile/bot.BotOne / getBotMove() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R175 | 16 | Must return Java objects responses to calling modules | Gamefile/page.PageManager / generateResponse() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R176 | 16 | Page Manager should support retry logic for failed communications | Gamefile/Code.GameManager/Files |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R177 | 16 | Setep up oour file in git hub to work properly | Gamefile/page.PageManager / retryCommunication() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R178 | 16 | Share Player information with Pair up | Gamefile/pairup.PairUp / assignPlayers() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R179 | 16 | Share GameSession,Position and Move with Game Play | Gamefile/play.GamePlay / routeToGamePlay() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R180 | 16 | Share Position,Move with Bot 1 and Bot 2 | Gamefile/bot.BotOne / sendMoveToBot(int botId) |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R181 | 16 | Share Position,Move,Session,Move and Player with Page maneger | Gamefile/page.PageManager / retryCommunication() |  | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R182 | 15 | Manage an internal list of active lobbies, each with a unique lobby ID. | uta.cse3310.PairUp.module.PairUpModule: field private List<Lobby> activeLobbies |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: lobby will show 1 player; Testing Group 22: not testable
R183 | 15 | Support lobbies containing up to two participants (human or bot). | uta.cse3310.PairUp.module.Lobby: private Participant[] slots = new Participant[2] |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: lobby will show 1 player; Testing Group 22: not testable
R184 | 15 | Create a new lobby with one human player in the first slot. | uta.cse3310.PairUp.module.PairUpModule#createLobby(String playerId) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R185 | 15 | Join an existing lobby by placing a player into the second slot if vacant. | uta.cse3310.PairUp.module.PairUpModule#joinLobby(String lobbyId, String playerId) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R186 | 15 | Create a lobby pre-filled with one human and one bot, then close the lobby. | uta.cse3310.PairUp.module.PairUpModule#createBotLobby(String playerId) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: Lobby created with human and bot,; Testing Group 22: not testable
R187 | 15 | Automatically mark a lobby as closed when it has two participants. | uta.cse3310.PairUp.module.PairUpModule#checkLobbyFull(Lobby lobby) and lobby.setClosed(true) in createBotLobby() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R188 | 15 | Notify the Game Manager when a lobby becomes full or a bot lobby is created. | uta.cse3310.PairUp.module.PairUpModule#notifyGameManager(Lobby lobby) in checkLobbyFull() and createBotLobby() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R189 | 15 | Handle a user quitting: remove lobby if empty or update/notify subscribers otherwise. | uta.cse3310.PairUp.module.PairUpModule#handleUserQuit(String lobbyId, String playerId) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: show open lobbies; Testing Group 22: not testable
R190 | 15 | Return a list of all open (non-closed) lobbies with IDs and occupant details. | uta.cse3310.PairUp.module.PairUpModule#refreshLobbies() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R191 | 15 | Reject join requests with LobbyException if the lobby is full, closed, or not found. | uta.cse3310.PairUp.module.PairUpModule#joinLobby throwing LobbyException |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R192 | 15 | Cancel an open lobby and notify subscribers of cancellation. | uta.cse3310.PairUp.module.PairUpModule#cancelLobby(String lobbyId) with call to notifySubscribers(...) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R193 | 15 | Optionally persist or update lobby data to a database. | uta.cse3310.PairUp.module.PairUpModule#storeOrUpdateLobby(Lobby lobby) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R194 | 15 | Enforce a maximum of 10 active lobbies; reject new creations when limit reached. | private static final int MAX_LOBBIES = 10 and checks in createLobby() and createDoubleBotLobby() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R195 | 15 | Remove lobbies idle for over 5 minutes (300,000 ms) and notify subscribers. | uta.cse3310.PairUp.module.PairUpModule#removeIdleLobbies() using IDLE_TIMEOUT and notifySubscribers(...) |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R196 | 15 | Automatically merge two idle human-only lobbies into a new closed lobby and notify game manager/subscribers. | uta.cse3310.PairUp.module.PairUpModule#checkIdlePlayersFromDifferentLobbies() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R197 | 15 | Define Lobby with fields: lobbyId, slots[2], closed flag, and creationTime. | Class uta.cse3310.PairUp.module.Lobby |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R198 | 15 | Define Participant with fields: playerId (nullable) and isBot. | Class uta.cse3310.PairUp.module.Participant |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 16: not testable; Testing Group 22: not testable
R199 | 15 | Provide PairUp entry-point accepting a DB instance and exposing getPairUpModule(). | Class uta.cse3310.PairUp.PairUp constructor and getPairUpModule() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R200 | 15 | Provide PageManager with Method to return opponents & status | uta.cse3310.PairUp.module.PairUpModule#pairPlayer() |  | not testable | Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R201 | 12 | The system displays the leaderboard to all players after each game. | cse3310/checkers/src/main/webapp/Leaderboard/leaderboard.html | #VALUE! |  | Group 9: FAIL, TC201; Group 11: Can not test since Login page is not working; Group 12: cannot test, since login is not working and cannot play game; Testing Group 14: could not test, unable to login; Testing Group 22: no.
R202 | 12 | The system retrieves leaderboard data from the database after game ends. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R203 | 12 | The system uses WebSocket to receive leaderboard updates from the Java backend. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R204 | 12 | The system formats and displays leaderboard data using HTML/JS only (no game logic in JS). | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! |  | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: cannot test, since cannot play game and cannot see leaderboard; Testing Group 14: could not test, unable to login; Testing Group 22: no.
R205 | 12 | JSON must be used for all communication between frontend and backend. | cse3310/checkers/src/main/webapp/Leaderboard/leaderboard.html | #VALUE! | not testable | Group 9: not testable; Group 11: Can not test since Login page is not working; Group 12: not testable; Testing Group 14: not testable; Testing Group 22: not testable
R206 | 12 | The Summary UI section must be part of a single-page HTML interface. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! |  | Group 9: FAIL, TC206; Group 11: Can not test since Login page is not working; Group 12: cannot test, since signup and login is not working; Testing Group 14: could not test, unable to login; Testing Group 22: Login is not working
R207 | 12 | The Summary section's visibility is controlled using showContent() and hideContent() functions which toggle display via CSS. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! |  | Group 9: FAIL, TC207; Group 11: Can not test since Login page is not working; Group 12: cannot test, since signup and login is not working; Testing Group 14: could not test, unable to login; Testing Group 22: not able to test login is not working
R208 | 12 | Each Summary client must have a unique identifier. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! |  | Group 9: FAIL, TC208; Group 11: Can not test since Login page is not working; Group 12: cannot test, since signup and login is not working; Testing Group 14: could not test, unable to login; Testing Group 22: no.
R209 | 12 | The leaderboard must auto-update when new game results are available. | cse3310/checkers/src/main/webapp/Leaderboard/summary.js | #VALUE! |  | Group 9: FAIL, TC209; Group 11: Can not test since Login page is not working; Group 12: cannot test, since signup and login is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R210 | 12 | The leaderboard shall display player statistics such as number of wins and losses. | cse3310/checkers/src/main/webapp/Leaderboard/leaderboard.html | #VALUE! |  | Group 9: FAIL, TC210; Group 11: Can not test since Login page is not working; Group 12: cannot test, since signup and login is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R211 | 23 | The Game must follow the rules the official rules of English draughts | GameTermination.checkForGameEnd(), hasAnyValiMoves() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R212 | 23 | The System shall support 10 consecutive games | GameTermination.checkForGameEnd() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R213 | 23 | After a game concludes players go to the end of the line | GameTermination.checkForGameEnd() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R214 | 23 | A leaderboard will be displayed after each game | GameTermination.checkForGameEnd() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot join game,; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R215 | 23 | Results of every game played must be stored in a database |  |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R216 | 23 | No game login in HTML/JS; all in java |  |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R217 | 23 | Java Subsystems communicate via methid calls | GameManager → checkForGameEnd() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R218 | 23 | After each move the state is processed and sent ti the client | checkForGameEnd(), hasAnyValidMoves(), countPieces() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R219 | 23 | Java is event driven | checkForGameEnd() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R220 | 23 | Return GameStatus enum in based on board state and move history | checkForGameEnd(BoardState, List <Move>) |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R221 | 23 | The system shall detect if a player no legal moves left | GameTermination.hasAnyValidMoves() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, login and signup is not working; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R222 | 23 | The system shall detec draw by 40-move rule | GameTermination.is40moveRuleDraw() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R223 | 23 | The system shall detect draw by 25 king-only non-capturing moves | GameTermination.check25MoveRuleKingOnly() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, cannot join game; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R224 | 23 | The system shall detect draw due to threefold board state repetition | GameTermination.checkForThreefoldRepetition() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot test, cannot join game; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R225 | 23 | The system shall detect mutual stalemate when both players cannot move | GameTermination.hasAnyValidMoves() |  |  | Group 11: Can not test since Login page is not working; Group 12: cannot join game, therefore cannot test it; Testing Group 14: could not test, unable to login; Testing Group 22: could not test, unable to login
R226 | 13 | The system must parse JSON data received from the Login Page and use it to star the user sessions. | handleLogin() |  |  | Group 11: 1) go to .\checkers\src\main\java\uta\cse3310\GameTermination\,2) click on the GameTermination java file 3)scroll down until hasValidMoves() function is found; Testing Group 22: could not test, unable to login
R227 | 13 | The system must receive and process game status from the Game Manager to update the frontend. | handleGameMove() |  |  | Testing Group 22: could not test, unable to login
R228 | 13 | The system must process user input from the Join Game Page to begin the pairing. | handleJoinGame() |  |  | Testing Group 22: could not test, unable to login
R229 | 13 | The system must forward input from the Join Game Page to the Pair Up system to initiate game setup. | handleJoinGame() |  |  | Testing Group 22: could not test, unable to login
R230 | 13 | The system must request and receive user profile data (including UserID, Wins, and Losses) from the database as a JSON object. | handleLogin() |  |  | Testing Group 22: could not test, unable to login
R231 | 13 | The system must receive game move data from the Game Manager in object format for client-side. | handleGameMove() |  |  | Testing Group 22: could not test, unable to login
R232 | 13 | The system must receive and handle object data for the leaderboard from the database and render it to the UI. | handleSummaryRequest() |  |  | Testing Group 22: could not test, unable to login
R233 | 13 | Page will transition between pages (Login, Join Game, Game View, Leaderboard) based on websocket events and internal state. | ProcessInput() |  |  | Testing Group 22: could not test, unable to login
R234 | 13 | All user interface updates will be handled in JavaScript/HTML/CSS and game logic on the java server side. | Handled by frontend (JS/CSS) and backend (Java: PageManager, GameManager) |  |  | Testing Group 22: could not test, unable to login
R235 | 13 | Websockets will be used for communication between the Java backend, Database and JavaScript frontend. | Implied via UserEvent & UserEventReply messaging structure |  |  | Testing Group 22: could not test, unable to login